COS 484 NLP Project Proposals

Seven proposal drafts aligned to the course template

Prepared using the same structure as the sample proposal: paper name, study type, codebase, timing/resources, and timeline.

Important note on compute estimates: where a paper or repo explicitly reported wall-clock, GPU/CPU count, or memory, I used those numbers directly. Where a paper did not report wall-clock, I marked the proposal estimate as an estimate based on the published workload (dataset size, number of seeds, prompt permutations, batch sizes, or epochs).

At-a-glance feasibility summary

| Paper | Exact paper-scale repro | Laptop-friendly scoped version | Main bottleneck | Overall course fit |
| --- | --- | --- | --- | --- |
| Data Mixture Inference | Moderate | Borderline | CPU + pair counting + Gurobi | Good if you want a tokenizer-focused project |
| The Reversal Curse | Hard | Yes | Original paper relies on API / large-model finetuning | Good if you want a clean synthetic experiment |
| Rethinking the Role of Demonstrations | Moderate | Yes | Large inference grid | Very good if you keep a small model/task subset |
| LoRA | Hard | Not really on laptop | GPU memory and sweep size | Useful but least practical under course constraints |
| Calibrate Before Use | Easy | Yes | Inference sweeps only | Excellent practical project |
| Fantastically Ordered Prompts | Moderate | Partly | Many prompt permutations | Good if you like prompting/ICL |
| SetFit | Very easy | Yes | Minimal | Best pure course-project fit |

Proposal 1. Data Mixture Inference: What do BPE Tokenizers Reveal about their Training Data?

Paper link: https://arxiv.org/abs/2407.16607    Codebase: https://github.com/alisawuffles/tokenizer-attack

Type of study: Both: baseline reproduction and model ablation/analysis study.

Project angle: This is the best proposal if the team wants a tokenizer/data-forensics project rather than a standard downstream classification project.

Baselines and new baselines

• Reproduce one controlled experiment from the paper on known mixtures, preferably a 5-way English-domain setup or a 5-way language setup rather than the largest 112-language setting.

• Run the paper’s two baselines - tokenizer encoding efficiency (TEE) and vocabulary item categorization (VIC) - against the main attack on the same controlled mixtures.

• Add a smaller-data baseline by training tokenizers on 1 GB/category instead of the paper’s 10 GB/category setting, to quantify how quickly attack quality degrades when compute is limited.

• Add a simpler feature baseline that only uses the top-T merge counts without the full solver, to test whether most of the signal already sits in the head of the merge list.

Proposed ablations / analyses

• Ablate the number of merges used by the attack: top 1k, 5k, 10k, 50k merges.

• Ablate tokenizer vocabulary size / number of BPE merges used during tokenizer training, which the paper does not treat as the main experimental knob.

• Ablate pretokenization assumptions: run the attack with the correct pretokenizer, with mildly wrong assumptions, and with clearly wrong assumptions to measure brittleness in a realistic attack setting.

• Ablate overlap across categories by deliberately adding shared boilerplate or duplicated documents across domains to test whether the attack still separates the mixtures.

Estimate of timing and computational resources

• Paper-scale reference: the paper states that all experiments were run on CPUs; training a tokenizer on 10 GB of data usually takes around 10 minutes, pair counting takes between 1 minute and 2 hours depending on the data, and the authors used 16-32 CPUs with 4-64 GB RAM plus Gurobi.

• Course-scale plan: for a scoped project, use 5 categories and 1 GB/category on a workstation or strong laptop. Expect roughly 15-45 minutes per tokenizer run on an 8-core to 16-core machine with 16-32 GB RAM, plus a few minutes for solving. A 20-run sweep should fit in roughly 8-20 CPU-hours.

• Dataset note: data are public and easy to obtain from Oscar and RedPajama/GitHub splits, but the project is still heavier than the few-shot prompting papers because preprocessing and pair counting dominate runtime.

Proposed timeline and division of work

• Week 1 - Set up preprocessing pipeline, download 5 categories, reproduce one paper baseline end-to-end. (Person 1: data, Person 2: tokenizer training, Person 3: solver/evaluation)

• Week 2 - Reproduce TEE and VIC baselines and verify main controlled result.

• Week 3 - Run merge-count and vocabulary-size ablations.

• Week 4 - Run pretokenization/overlap robustness ablations and summarize failure modes.

• Week 5 - Write paper, prepare figures, and finalize presentation.

Recommended scope note: This proposal is feasible, but it is more systems-heavy than the prompting papers because preprocessing and counting dominate runtime.

Proposal 2. The Reversal Curse: LLMs trained on 'A is B' fail to learn 'B is A'

Paper link: https://arxiv.org/abs/2309.12288    Codebase: https://github.com/lukasberglund/reversal_curse

Type of study: Both: baseline reproduction and ablation/analysis study.

Project angle: This is the cleanest synthetic reasoning project. It is conceptually strong, and the dataset is tiny.

Baselines and new baselines

• Reproduce Experiment 1 at small scale with an open model (GPT-2 small/medium or a similarly sized decoder LM) using the released synthetic data generation pipeline.

• Measure same-order exact-match accuracy versus reverse-order exact-match accuracy, which is the core baseline from the paper.

• Add a full-finetuning versus LoRA baseline on the same small open model. This is not in the original paper and directly tests whether the curse is tied to full-parameter memorization.

• Add a no-paraphrase baseline versus paraphrase-augmented training to mirror one of the paper’s robustness checks on a smaller model.

Proposed ablations / analyses

• Mask loss on prompt tokens versus train on the full sequence. This is a genuinely new ablation and directly tests whether the model is learning a directional next-token pattern rather than a symmetric association.

• Ablate training format: isolated factual sentences versus short structured biographies or QA-style mini-documents. This tests whether richer discourse helps reversal emerge.

• Ablate answer position: same fact but with the name at the end versus in the middle of the sentence.

• Ablate dataset symmetry pressure: train with 0%, 10%, 25%, and 50% both-direction auxiliary facts to see whether there is a threshold where reverse generalization starts to appear.

Estimate of timing and computational resources

• Paper-scale reference: the released synthetic dataset contains 30 facts with 30 paraphrases each, i.e. 900 documents per subset; the GPT-3 sweep trains for 10 epochs, and the paper reports that Llama-30B runs used eight A100 GPUs for roughly 20-160 minutes per epoch depending on batch size. The paper also notes that the OpenAI API sweeps cost about $100 per experiment.

• Course-scale plan: with a small open model and the same tiny synthetic dataset, one run should fit on a single 12-16 GB GPU. Expect about 10-25 minutes per training run including evaluation, and roughly 6-10 GPU-hours for a meaningful sweep of 20-30 runs.

• Dataset note: the data are tiny and synthetic, so this project is very easy to iterate on once the training loop is working.

Proposed timeline and division of work

• Week 1 - Reproduce the released synthetic-data setup on one small model. (Person 1: data/prompt pipeline, Person 2: training loop, Person 3: evaluation)

• Week 2 - Establish same-order versus reverse-order baselines and LoRA/full-finetune comparison.

• Week 3 - Run loss-masking and discourse-format ablations.

• Week 4 - Run symmetry-pressure ablations and analyze when reversal starts, if at all.

• Week 5 - Write paper and prepare qualitative examples for presentation.

Recommended scope note: Do not promise exact GPT-3 or Llama-30B reproduction in the proposal unless you truly have API budget or multi-A100 access.

Proposal 3. Rethinking the Role of Demonstrations: What Makes In-Context Learning Work?

Paper link: https://arxiv.org/abs/2202.12837    Codebase: https://github.com/Alrope123/rethinking-demonstrations

Type of study: Both: baseline reproduction and analysis study.

Project angle: A very good project if the team wants an in-context learning paper with many natural follow-up experiments and no training of large models.

Baselines and new baselines

• Reproduce a scoped subset of the paper: 4-5 classification datasets, GPT-2 Large, and the channel method only.

• Reproduce the paper’s three core conditions: no demonstrations, demonstrations with gold labels, and demonstrations with random labels.

• Reproduce the paper’s k-shot scaling on a smaller set of datasets using k in {4, 8, 16, 32}.

• Add a nearest-neighbor retrieval baseline for choosing demonstrations instead of uniform random sampling.

Proposed ablations / analyses

• Ablate class balance of demonstrations: naturally sampled versus perfectly balanced demonstration sets.

• Ablate position-specific label corruption: corrupt only the first example, only the last example, half the examples, or all examples. This isolates whether certain demonstration positions matter more.

• Ablate label semantics: use natural label words, arbitrary label IDs, and semantically misleading label words.

• Ablate similarity/diversity trade-off in demonstration selection: most similar, most diverse, and mixed retrieval.

Estimate of timing and computational resources

• Paper-scale reference: the paper evaluates 12 models on 26 datasets, all with fewer than 10K training examples by design; the repo supports GPT-2 Large, MetaICL, GPT-J, and GPT-3, notes that inference is single-GPU only, and suggests batch sizes sized for a 32 GB GPU.

• Course-scale plan: keep only GPT-2 Large, 4-5 classification datasets, 3 seeds, and the channel method. Expect roughly 10-20 minutes per dataset/seed/condition on one 24-32 GB GPU, giving a total budget of around 8-15 GPU-hours for the full project sweep.

• Dataset note: all datasets are public and small; the main bottleneck is the size of the inference grid, not data loading or training.

Proposed timeline and division of work

• Week 1 - Set up repo, pick 4-5 datasets, reproduce one dataset end-to-end. (Person 1: dataset setup, Person 2: model/inference, Person 3: analysis scripts)

• Week 2 - Reproduce no-demo / gold-label / random-label results on all chosen datasets.

• Week 3 - Run class-balance and position-specific corruption ablations.

• Week 4 - Run label-semantics and retrieval-strategy ablations.

• Week 5 - Consolidate results, write paper, and prepare slides.

Recommended scope note: This can realistically be executed within a normal course-project budget if the scope is kept to the subset described above.

Proposal 4. LoRA: Low-Rank Adaptation of Large Language Models

Paper link: https://arxiv.org/abs/2106.09685    Codebase: https://github.com/microsoft/LoRA

Type of study: Both: baseline reproduction and ablation study.

Project angle: This is the most famous paper in the list, but it is also the least laptop-friendly unless you deliberately scope it to small GLUE tasks and moderate backbones.

Baselines and new baselines

• Do not attempt GPT-3 175B reproduction. Scope the project to RoBERTa-large on 2-3 GLUE tasks such as SST-2, MRPC, and RTE.

• Compare full fine-tuning, classifier-head-only fine-tuning, BitFit, and LoRA on the same backbone.

• Use the paper’s standard LoRA settings as the main baseline, then vary rank r and target matrices.

• Optionally add a frozen-encoder + logistic regression baseline for a stronger low-compute reference.

Proposed ablations / analyses

• Ablate rank r in {1, 2, 4, 8, 16}.

• Ablate target placement: query/value only, all attention projections, attention plus MLP, or top-half layers only.

• Ablate LoRA dropout and scaling alpha to measure robustness in very small-data settings.

• Ablate few-shot versus full-data fine-tuning to test whether LoRA helps more when labels are scarce.

Estimate of timing and computational resources

• Paper-scale reference: the LoRA paper spans RoBERTa, DeBERTa, GPT-2, and GPT-3; it uses NVIDIA Tesla V100 GPUs throughout and reports a 25% training-speed improvement for GPT-3 175B, with throughput increasing from 32.5 to 43.1 tokens/s per V100 GPU. The original GPT-3 experiments are not realistic for a course project.

• Course-scale plan: with RoBERTa-large on SST-2, MRPC, and RTE, one run should fit on a single 16-24 GB GPU with mixed precision. Expect about 30-45 minutes for SST-2 and about 5-10 minutes each for MRPC and RTE, so a 3-task configuration sweep typically costs 1-2 GPU-hours per setting.

• Dataset note: GLUE tasks are trivial to obtain, but this paper is still not a laptop-first choice because even the scoped version benefits strongly from a real GPU.

Proposed timeline and division of work

• Week 1 - Reproduce one LoRA run on one GLUE task. (Person 1: data, Person 2: training code, Person 3: baseline implementations)

• Week 2 - Establish full-finetune / head-only / BitFit / LoRA baselines on 2-3 tasks.

• Week 3 - Run rank and target-module ablations.

• Week 4 - Run dropout / alpha / few-shot versus full-data ablations.

• Week 5 - Write paper and summarize trade-offs between quality and parameter efficiency.

Recommended scope note: Only choose this paper if the team has reliable GPU access; otherwise the scoped GLUE-only version is the maximum practical plan.

Proposal 5. Calibrate Before Use: Improving Few-Shot Performance of Language Models

Paper link: https://arxiv.org/abs/2102.09690    Codebase: https://github.com/tonyzhaozh/few-shot-learning

Type of study: Both: baseline reproduction and ablation study.

Project angle: One of the best practical course-project options. No training is required for the main experiments, the repo is clean, and the paper already exposes clear variance problems to build on.

Baselines and new baselines

• Reproduce GPT-2 XL results on 4-5 text-classification datasets for 0, 1, 4, and 8 shots.

• Compare the uncalibrated baseline with contextual calibration exactly as in the paper.

• Add a simple prior-correction baseline that only normalizes by class frequency in the prompt, which is weaker than full contextual calibration but strong enough to be informative.

• Add an identity-W / bias-only correction baseline for local models, since the paper notes an alternate correction view but does not make it a central classification baseline.

Proposed ablations / analyses

• Ablate the content-free input set: empty string, N/A, [MASK], gibberish string, and short neutral sentence.

• Ablate prompt label imbalance and order to test whether calibration helps equally when the prompt is badly skewed.

• Ablate verbalizer choice: natural labels versus shortened labels or arbitrary tokens.

• Ablate calibration transfer: compute calibration from one template and test it on another template for the same task.

Estimate of timing and computational resources

• Paper-scale reference: the paper uses labeling budgets up to 8 shots because querying larger settings via the OpenAI API became prohibitively expensive. The official repo states that the experiments are relatively lightweight, require no training, and need only a single GPU for local models such as GPT-2.

• Course-scale plan: for GPT-2 XL on 5 datasets, 4 shot settings, and 3-5 seeds, expect roughly 3-8 GPU-hours total on a single 16 GB to 24 GB GPU, because each run is just forward inference over a subsampled test set.

• Dataset note: all core datasets are public and easy to load; this project is very feasible on a laptop if you swap GPT-2 XL for a smaller local model, though slower.

Proposed timeline and division of work

• Week 1 - Run one dataset end-to-end and verify baseline/calibrated numbers. (Person 1: prompts/datasets, Person 2: inference code, Person 3: analysis)

• Week 2 - Reproduce baseline versus contextual calibration on all chosen datasets.

• Week 3 - Run content-free input and verbalizer ablations.

• Week 4 - Run imbalance/order and template-transfer ablations.

• Week 5 - Write paper and create plots showing variance reduction.

Recommended scope note: This can realistically be executed within a normal course-project budget if the scope is kept to the subset described above.

Proposal 6. Fantastically Ordered Prompts and Where to Find Them: Overcoming Few-Shot Prompt Order Sensitivity

Paper link: https://arxiv.org/abs/2104.08786    Codebase: https://github.com/yaolu/ordered-prompt

Type of study: Both: baseline reproduction and ablation study.

Project angle: A strong prompt-engineering / ICL project. It is inference-only but the permutation budget can still become expensive if not scoped.

Baselines and new baselines

• Reproduce a scoped version of the paper on 3-4 datasets such as SST-2, CR, TREC, and AGNews.

• Compare random prompt order, LocalE, GlobalE, and oracle order selection.

• Use one or two local GPT-2 family models rather than the entire GPT-2/GPT-3 size ladder.

• Add a random-search baseline with the same prompt-selection budget as LocalE/GlobalE.

Proposed ablations / analyses

• Ablate probing-set size: 32, 64, 128, and 256 unlabeled examples.

• Ablate n-gram length and entropy statistics used inside the scoring rule; the public scripts already expose n = 3 and 5, so this is easy to extend.

• Ablate simple heuristic orders such as alternating labels, grouping by label, or ordering by example length.

• Ablate transfer across templates: pick the best order under one template and test it under another.

Estimate of timing and computational resources

• Paper-scale reference: the paper studies 24 prompt permutations for 4-shot settings, reports results across eleven text-classification tasks, and sub-samples 256 validation examples specifically to control GPT-3 inference costs because the GPT-3 API was paid.

• Course-scale plan: with GPT-2 Large or GPT-2 XL on 3-4 datasets and 3 seeds, expect roughly 30-90 minutes per dataset/model/seed once prompt-generation, probing, and evaluation are included. A complete scoped project should fit in roughly 8-16 GPU-hours.

• Dataset note: datasets are small and public. The difficulty is not the data; it is the number of permutations and scoring passes.

Proposed timeline and division of work

• Week 1 - Reproduce one dataset with random order, LocalE, GlobalE, and oracle. (Person 1: prompt pipeline, Person 2: inference/scoring, Person 3: evaluation)

• Week 2 - Extend to 3-4 datasets and verify trend consistency.

• Week 3 - Run probing-set-size and n-gram ablations.

• Week 4 - Run heuristic-order and template-transfer ablations.

• Week 5 - Write paper and prepare error analysis examples.

Recommended scope note: This can realistically be executed within a normal course-project budget if the scope is kept to the subset described above.

Proposal 7. SetFit: Efficient Few-Shot Learning Without Prompts

Paper link: https://arxiv.org/abs/2209.11055    Codebase: https://github.com/huggingface/setfit

Type of study: Both: baseline reproduction and ablation study.

Project angle: This is the best pure course-project fit: public code, public datasets, very low training cost, and many clean hyperparameter ablations.

Baselines and new baselines

• Reproduce SetFit on 3-6 public datasets with N = 8 and N = 64 labels per class.

• Compare SETFITMPNET against three simple baselines: frozen sentence-transformer + logistic regression, full fine-tuning of the same sentence-transformer backbone, and a nearest-centroid classifier on frozen embeddings.

• Add a smaller-model baseline with MiniLM to quantify the accuracy/efficiency trade-off.

• Optionally include a standard prompt-based baseline only on one dataset, just to show why a prompt-free method is attractive.

Proposed ablations / analyses

• Ablate the sentence-transformer backbone: MPNet versus MiniLM.

• Ablate the contrastive fine-tuning stage: number of generated training pairs and pair-sampling strategy.

• Ablate the classification head: logistic regression versus a small neural head.

• Ablate number of epochs and learning rate for the contrastive stage.

Estimate of timing and computational resources

• Paper-scale reference: the paper fine-tunes the ST model for 1 epoch with learning rate 1e-3, batch size 16, and maximum length 256; it also reports that SETFITMPNET takes about 30 seconds to train on N = 8 examples using a p3.2xlarge AWS instance with 16 GB GPU memory.

• Course-scale plan: one run on a single 8-16 GB GPU should be well under 1 minute for N = 8 and just a few minutes for N = 64. Even a 20-40 run ablation sweep should fit comfortably in roughly 2-4 GPU-hours. On CPU, it is still feasible on a laptop, just slower.

• Dataset note: the datasets are public on the Hugging Face Hub under the SetFit organization, so data access is essentially frictionless.

Proposed timeline and division of work

• Week 1 - Reproduce one dataset and verify that training really is fast. (Person 1: datasets, Person 2: training code, Person 3: baselines/plots)

• Week 2 - Reproduce SetFit on all chosen datasets with N = 8 and N = 64.

• Week 3 - Run backbone and classifier-head ablations.

• Week 4 - Run pair-generation and optimization hyperparameter ablations.

• Week 5 - Write paper and prepare a compact, polished presentation.

Recommended scope note: This can realistically be executed within a normal course-project budget if the scope is kept to the subset described above.